CREATIVE CONQUEST

Client Onboarding Checklist

Run this the moment a deposit clears. Target: client fully set up and first content day booked within 14 days. Owner = Account & Content Lead (the Conductor).

| Client / Practice | _______________________________ |
| --- | --- |
| Primary contact | _______________________________ |
| Email / phone | _______________________________ |
| Tier | Foundation / Growth / Authority |
| Deposit paid | _____________ ($1,500 reserves slot, content day & launch pricing) |
| Start date | _____________ |
| Content day (date) | _____________ |
| Owner (seat) | Account & Content Lead |

# 1 · Pre-Kickoff (within 24 hours of deposit)

- Send welcome email + receipt and confirm the reserved slot

- Create client folder in Google Drive (Raw / Edited / Brand / Approved)

- Create client vault entry in Bitwarden for shared logins

- Add client + deal to GoHighLevel pipeline; move stage to 'Onboarding'

- Send the intake form (links below) and brand-asset request

- Schedule the kickoff call (30 min) and the content day

# 2 · Access & Logins

Collect via Bitwarden — never over email or text. Request admin or editor access, not the client's personal password where a team seat exists.

- Instagram (Reels) — login or added as collaborator

- TikTok — login or team access

- YouTube (Shorts) — channel manager access

- LinkedIn (Authority tier only)

- Meta Business Suite / Buffer connected for scheduling

- Confirm 2FA recovery method is documented in the vault

# 3 · Brand Kit & Assets

- Logo files (PNG + vector)

- Brand colors (hex) and fonts

- Existing photos / b-roll / past videos

- Tone & voice notes — what they will and won't say

- Treatment / service list with correct medical terminology

- Compliance no-go list (claims they cannot make)

- Build the Canva brand kit (colors, fonts, caption templates, thumbnail templates)

# 4 · Strategy & Content Plan

- Confirm target client & the 'gap we fill' (premium, well-reviewed, invisible on video)

- Agree the content pillars (Education, Myth-Buster, Demo, Patient Result, FAQ, etc.)

- Set platform mix per tier (Foundation 1+repurpose, Growth 2-3, Authority all + LinkedIn)

- Set monthly volume (Foundation 12 / Growth 20 / Authority 30+)

- Draft first 20 video concepts in the Content Production Tracker

- Confirm posting cadence (~5/week) and best posting windows

# 5 · Content Day Logistics

- Confirm date, location, and on-camera talent (provider)

- Send shot list & talking-point prompts in advance

- Equipment ready: phone, $30 tripod, clip mic, lighting check

- Wardrobe / setting / signage guidance sent

- Plan to film a full month (20+) in one session

- Backup: footage uploaded to Drive same day

# 6 · Systems Setup

- Stripe / PayPal subscription set to monthly tier price

- Recurring invoice / billing date confirmed

- GoHighLevel calendar + pipeline live for this client

- ROI report template duplicated and labeled for this client

- Engagement window scheduled (daily comments & first-reply DMs)

# 7 · Kickoff Call Agenda (30 min)

- Re-state the promise: booked calendar + bought-back time, no ad spend

- Walk through the 90-day arc and what month 1 looks like

- Confirm content day and what they need to prepare

- Set expectations: they film once/month, we run the engine

- Restate the guarantee (satisfaction-based on quality — never an income promise)

- Agree the monthly ROI report + call cadence

# 8 · Week 1 — First Proof

- First batch edited in CapCut and polished in Canva

- QA pass against the brand standard

- Client approval on first 3-5 videos

- Scheduled in Buffer / Meta Suite

- First post live — overdeliver early

- Move GoHighLevel stage to 'Active / Delivering'

“Where focus goes, energy flows.”